## Sprint 3
| Sprint 3 | Date début | 2017-03-05
| Scholar Net | Date de fin (inclus) | 2017-03-17 |  | 513334 |  | 42498.6067
|  | Effort Scrum Initial | 49
|  | Objectifs du sprint | Construire le début de l'application et l'espace personnel de l'utilisateur avec l'ajout de publications.
ID | Nom | Valeur/Importance | Estimation Initiale | 2008-07-21 | 2008-07-22 | 2008-07-23 | 2008-07-24 | 2008-07-25 | 2008-07-28 | 2008-07-29 | 2008-07-30 | 2008-07-31 | 2008-08-01
27 | Integration sur Github et coordination des parties de chacun | 92 | 8 | 8 | 8 | 7 | 6 | 6 | 4 | 4 | 3 | 2 | 0
25 | Regler les bugs | 93 | 20 | 20 | 18 | 16 | 16 | 10 | 8 | 8 | 4 | 4 | 0
25 | Effectuer des tests | 93 | 15 | 15 | 13 | 13 | 13 | 13 | 8 | 7 | 7 | 4 | 0
20 | Validation Javascript de tous les formulaires | 83 | 6 | 6 | 6 | 6 | 4 | 4 | 4 | 4 | 2 | 0 | 0
|  |  | 49 | 49 | 45 | 42 | 39 | 33 | 24 | 23 | 16 | 10 | 0 | <= Unités Scrum Restantes
|  |  | Prévision | 152 | 135.1111 | 118.2222 | 101.3333 | 84.4444 | 67.5556 | 50.6667 | 33.7778 | 16.8889 | 0 | 0
Note on B6: Reuters Financial Software: Insert here a quick and short descriptive name for the story. Clear enough so that developers understand what we are talking about and clear enough to distinguish it from other stories. Usually 2 to 10 words
Note on C6: Reuters Financial Software: This is the product owner's importance rating for this story. The higher is the value, the more important is this story. There is no max value, and we tend to avoid to use "priority 1" cause if you later decide that something else is even more important, do you think you would put "priority 0" or "priority -1" ? ?
Note on D6: Reuters Financial Software: This is the team's initial assessment of how much work is needed to implement this story compared to other stories. The unit is story points and usually corresponds roughly to "ideal man days". The importance is to undertand that this is just a relative value that will be accurate if you compute-it with the Team's velocity. If a team velocity is 3 units / days then you can quickly figure-out when the req might be ready. This part (all green items) must be filled by KARMA developers only. Not by the product owner
Note on D15: nicolas.martignole: Initial total of Scrum units
Note on E16: nicolas.martignole: Edit this cell formula and make a link to the calculs Sheet so that the graph is generated automatically